## Risk Register
Risk ID | Asset | Threat | Vulnerability | Impact (Business) | Likelihood (1-3) | Impact (1-3) | Risk Score | ISO 27001 Control | Control Effectiveness | Mitigation | Residual Risk | Owner | Status
R1 | User Accounts | SQL Injection | No input validation | Unauthorized access to user data (GDPR risk) | 3 | 3 | 9 | A.14.2.5 | Ineffective | Use parameterized queries | Medium | Security Team | Open
R2 | Authentication System | Credential Stuffing | Weak password policy | Account takeover | 3 | 3 | 9 | A.9.4.2 | Partially Effective | Implement MFA | Medium | Security Team | Open
R3 | Database | Data Exposure | No encryption | Sensitive data leak | 2 | 3 | 6 | A.10.1 | Ineffective | Encrypt data at rest | Low | DevOps | Open
R4 | API | Broken Access Control | Missing authorization checks | Unauthorized data access | 3 | 3 | 9 | A.9.1.2 | Ineffective | Implement RBAC | Medium | Backend Team | Open
R5 | Logging System | Lack of monitoring | No alerting | Delayed incident detection | 2 | 3 | 6 | A.12.4.1 | Ineffective | SIEM + alerts | Low | SecOps | Open